## Sheet1
Core Functional Modules |  | May | June |  |  |  |  | July |  |  |  | August |  |  |  | September
|  | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
UI / FRONTEND FOUNDATION | bar: May Week 4 to June Week 1
DATABASE & CORE BACKEND | bar: May Week 4 to June Week 1
Profiles Module | Guest Profiles | bar: May Week 4 to June Week 3
Guest Linking | bar: May Week 4 to June Week 3
Guest History | bar: May Week 4 to June Week 3
VIP Guests | bar: May Week 4 to June Week 3
Reservation Module | Reservation Creation | bar: May Week 4 to June Week 3
Reservation Search | bar: May Week 4 to June Week 3
Reservation Editing | bar: May Week 4 to June Week 3
Reservation Status | bar: May Week 4 to June Week 3
Walk-In Handling | bar: May Week 4 to June Week 3
Room Assignment | bar: May Week 4 to June Week 3
Front Desk Operations | Arrivals Monitoring | bar: June Week 3 to June Week 5
In-House Monitoring | bar: June Week 3 to June Week 5
Check-In | bar: June Week 3 to June Week 5
Check-Out | bar: June Week 3 to June Week 5
Front Desk Dashboard | bar: June Week 3 to June Week 5
Billing Module | Folio Management | bar: June Week 4 to July Week 1
Charge Posting | bar: June Week 4 to July Week 1
Payment Processing | bar: June Week 4 to July Week 1
Invoice Generation | bar: June Week 4 to July Week 1
Settlement Workflow | bar: June Week 4 to July Week 1
Advanced Billing | Split Billing | bar: June Week 5 to July Week 1
Routing Charges | bar: June Week 5 to July Week 1
Deposit Handling | bar: June Week 5 to July Week 1
Folio History | bar: June Week 5 to July Week 1
Rooms Management | Room Status Monitoring | bar: July Week 1 to July Week 2
Housekeeping Status | bar: July Week 1 to July Week 2
Cleaning Workflow | bar: July Week 1 to July Week 2
Maintenance Flags | bar: July Week 1 to July Week 2
Room Conditions | bar: July Week 2 to July Week 3
Groups & Blocks | Group Reservations | bar: July Week 2 to July Week 3
Room Blocks | bar: July Week 2 to July Week 3
Rooming Lists | bar: July Week 2 to July Week 3
Group Billing | bar: July Week 2 to July Week 3
Advanced Reservation Features | Reservation Notes | bar: July Week 2 to July Week 4
Waitlist | bar: July Week 2 to July Week 4
Reservation Confirmation | bar: July Week 2 to July Week 4
Reservation Deposits | bar: July Week 2 to July Week 4
Add-On Reservations | bar: July Week 2 to July Week 4
Simulation Features | Event Generator | bar: July Week 4 to August Week 2
Simulation Config | bar: July Week 4 to August Week 2
Scenario Processing | bar: July Week 4 to August Week 2
Demo Reset Engine | bar: July Week 4 to August Week 2
Event Weight Controls | bar: July Week 4 to August Week 2
Training Environment | Simulation Mode | bar: August Week 1 to August Week 3
Live Mode | bar: August Week 1 to August Week 3
Training Workflows | bar: August Week 1 to August Week 3
Operational Replay | bar: August Week 1 to August Week 3
Reports & Analytics | KPI Dashboards | bar: August Week 2 to August Week 4
Revenue Reports | bar: August Week 2 to August Week 4
Occupancy Reports | bar: August Week 2 to August Week 4
Export to PDF/XLSX | bar: August Week 2 to August Week 4
Issues Bugfixing | bar: July Week 1 to September Week 4